## Sheet1
Project Name | Project Start Date |  |  |  | 2016-01-29 | Owners | Person Hrs Assigned
| Project End Date |  |  |  | 2016-02-15 | Sam | 0
| Total Person Hours |  |  |  | 47 | Harry | 0
[6 empty] | Ben | 24
Cell Color Legend | [5 empty] | Emmett | 23
Do Not Enter Data
Enter Data Here
Task Completed
Task Started
Task Not Started
Do Not Enter Data in Gantt Chart
| Task # | First Preceding Task # | Second Preceding Task # | Third Preceding Task # | Task Description | Owner | Percent Complete | Task Person Hours | Average Hours Per Day | Calcu-lated Duration in Days | Fixed Project Day Task Start | # Pred | ES1 | ES2 | ES3 | ES | EF | Calculated Task Start Day | Calculated Task End Day (COB) | Task # | Task Description | Owner | 2016-01-29 | 2016-01-30 | 2016-01-31 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-06 | 2016-02-07 | 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12 | 2016-02-13 | 2016-02-14 | 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19 | 2016-02-20 | 2016-02-21 | 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26 | 2016-02-27 | 2016-02-28 | 2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04 | 2016-03-05 | 2016-03-06 | 2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11 | 2016-03-12 | 2016-03-13 | 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18 | 2016-03-19 | 2016-03-20 | 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25 | 2016-03-26 | 2016-03-27 | 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08 | 2016-04-09 | 2016-04-10 | 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15 | 2016-04-16 | 2016-04-17 | 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22 | 2016-04-23 | 2016-04-24
| 1 |  |  |  | project kickoff | Ben | 100% |  |  | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 2016-01-29 | 2016-01-28 | 1 | project kickoff | Ben
| 2 | 1 |  |  | hardware inventory | Ben | 50% | 1 | 2 | 1 |  | 1 | 1 | 0 | 0 | 1 | 2 | 2016-01-29 | 2016-01-29 | 2 | hardware inventory | Ben
| 3 | 1 |  |  | parts research | Ben | 20% | 2 | 2 | 1 |  | 1 | 1 | 0 | 0 | 1 | 2 | 2016-01-29 | 2016-01-29 | 3 | parts research | Ben
| 4 | 1 |  |  | spec out parts | Ben | 0% | 2 | 2 | 1 |  | 1 | 1 | 0 | 0 | 1 | 2 | 2016-01-29 | 2016-01-29 | 4 | spec out parts | Ben
| 5 | 2 |  |  | order parts | Ben | 0% | 1 | 2 | 1 |  | 1 | 2 | 0 | 0 | 2 | 3 | 2016-01-30 | 2016-01-30 | 5 | order parts | Ben
| 6 | 5 |  |  | begin design | Ben | 0% | 4 | 2 | 2 |  | 1 | 3 | 0 | 0 | 3 | 5 | 2016-01-31 | 2016-02-01 | 6 | begin design | Ben
| 7 | 6 |  |  | assembly | Ben | 0% | 8 | 2 | 4 |  | 1 | 5 | 0 | 0 | 5 | 9 | 2016-02-02 | 2016-02-05 | 7 | assembly | Ben
| 8 | 7 |  |  | improve design | Ben | 0% | 4 | 2 | 2 |  | 1 | 9 | 0 | 0 | 9 | 11 | 2016-02-06 | 2016-02-07 | 8 | improve design | Ben
| 9 | 8 | 3 | 4 | Research software libraries | Emmett | 0% | 3 | 3 | 1 |  | 3 | 11 | 2 | 2 | 11 | 12 | 2016-02-08 | 2016-02-08 | 9 | Research software libraries | Emmett
| 10 | 9 |  |  | calibrating indivudal parts | Ben | 0% | 2 | 2 | 1 |  | 1 | 12 | 0 | 0 | 12 | 13 | 2016-02-09 | 2016-02-09 | 10 | calibrating indivudal parts | Ben
| 11 | 10 |  |  | Begin basic logic flow | Emmett | 0% | 4 | 2 | 2 |  | 1 | 13 | 0 | 0 | 13 | 15 | 2016-02-10 | 2016-02-11 | 11 | Begin basic logic flow | Emmett
| 12 | 6 | 10 |  | debugging/testing | Emmett | 0% | 12 | 3 | 4 | 10 | 2 | 5 | 13 | 10 | 13 | 17 | 2016-02-10 | 2016-02-13 | 12 | debugging/testing | Emmett
| 13 | 12 |  |  | fine tuning | Emmett | 0% | 4 | 2 | 2 |  | 1 | 17 | 0 | 0 | 17 | 19 | 2016-02-14 | 2016-02-15 | 13 | fine tuning | Emmett
| 14 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 14 | 0 | 0
| 15 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 15 | 0 | 0
| 16 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 16 | 0 | 0
| 17 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 17 | 0 | 0
| 18 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 18 | 0 | 0
| 19 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 19 | 0 | 0
| 20 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 20 | 0 | 0
| 21 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 21 | 0 | 0
| 22 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 22 | 0 | 0
| 23 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 23 | 0 | 0
| 24 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 24 | 0 | 0
| 25 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 25 | 0 | 0
| 26 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 26 | 0 | 0
| 27 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 27 | 0 | 0
| 28 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 28 | 0 | 0
| 29 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 29 | 0 | 0
| 30 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 30 | 0 | 0
| 31 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 31 | 0 | 0
| 32 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 32 | 0 | 0
| 33 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 33 | 0 | 0
| 34 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 34 | 0 | 0
| 35 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 35 | 0 | 0
| 36 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 36 | 0 | 0
| 37 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 37 | 0 | 0
| 38 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 38 | 0 | 0
| 39 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 39 | 0 | 0
| 40 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 40 | 0 | 0
| 41 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 41 | 0 | 0
| 42 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 42 | 0 | 0
| 43 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 43 | 0 | 0
| 44 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 44 | 0 | 0
| 45 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 45 | 0 | 0
| 46 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 46 | 0 | 0
| 47 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 47 | 0 | 0
| 48 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 48 | 0 | 0
| 49 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 49 | 0 | 0
| 50 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 50 | 0 | 0
| 51 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 51 | 0 | 0
| 52 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 52 | 0 | 0
| 53 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 53 | 0 | 0
| 54 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 54 | 0 | 0
| 55 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 55 | 0 | 0
| 56 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 56 | 0 | 0
| 57 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 57 | 0 | 0
| 58 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 58 | 0 | 0
| 59 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 59 | 0 | 0
| 60 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 60 | 0 | 0
| 61 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 61 | 0 | 0
| 62 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 62 | 0 | 0
| 63 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 63 | 0 | 0
| 64 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 64 | 0 | 0
| 65 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 65 | 0 | 0
| 66 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 66 | 0 | 0
| 67 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 67 | 0 | 0
| 68 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 68 | 0 | 0
| 69 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 69 | 0 | 0
| 70 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 70 | 0 | 0
| 71 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 71 | 0 | 0
| 72 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 72 | 0 | 0
| 73 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 73 | 0 | 0
| 74 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 74 | 0 | 0
| 75 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 75 | 0 | 0
| 76 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 76 | 0 | 0
| 77 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 77 | 0 | 0
| 78 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 78 | 0 | 0
| 79 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 79 | 0 | 0
| 80 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 80 | 0 | 0
| 81 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 81 | 0 | 0
| 82 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 82 | 0 | 0
| 83 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 83 | 0 | 0
| 84 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 84 | 0 | 0
| 85 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 85 | 0 | 0
| 86 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 86 | 0 | 0
| 87 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 87 | 0 | 0
| 88 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 88 | 0 | 0
| 89 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 89 | 0 | 0
| 90 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 90 | 0 | 0
| 91 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 91 | 0 | 0
| 92 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 92 | 0 | 0
| 93 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 93 | 0 | 0
| 94 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 94 | 0 | 0
| 95 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 95 | 0 | 0
| 96 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 96 | 0 | 0
| 97 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 97 | 0 | 0
| 98 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 98 | 0 | 0
| 99 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2016-01-28 | 2016-01-27 | 99 | 0 | 0
Note on G1: Use M/D/YYYY format to enter project start day.
Note on H1: List task owners below and use the same exact spelling under the Owner column to obtain total person hours assigned.
Note on G2: Project is completed at start of business on this day.
Note on H2: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.
Note on H3: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.
Note on H4: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.
Note on H5: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.
Note on H6: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.
Note on H7: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.
Note on C14: Task must be numbered in ascending order. Leave the lines blank for task numbers not used.
Note on D14: Use the task number of one of the up to three directly preceding tasks, the immediate task that must be completed before this task can start.
Note on E14: Use the task number of one of the up to three directly preceding tasks, the immediate task that must be completed before this task can start.
Note on F14: Use the task number of one of the up to three directly preceding tasks, the immediate task that must be completed before this task can start.
Note on G14: Give a brief task description / name here.
Note on H14: Provide name of the task owner, person responsible for task completion.
Note on I14: Enter percent complete for the task. Block color in Gantt exhibit changes to black to show 100% complete, green to show in progress.
Note on J14: Record person hours estimate to complete named task.
Note on K14: Record the average daily hours the owner will spend on this task adjusting for planned days off.
Note on L14: Calculated rounded up integer calendar days duration of the task based on person hours and daily hours on task.
Note on M14: Set day of project using days since project start to fix the task start day. Task will start this day or the calculated start day based on preceding tasks, whichever is later. You must set a day for tasks that have no preceding tasks.
Note on T14: Task start date at begiining of business day.
Note on U14: Calculated task ending date at close of business.
Note on H15: List task owner here using the same exact spelling under the Owner column to obtain total person hours assigned.